## Gxx-xxxx
Student Name: | DANIEL ALIZRAEE |  |  | Activity Log for Design Project 1 (Revision)
Full Student Number: | 301455251
Group Number: | G03
Members Relative Contribution: (estimate your contribution to this phase of the project) | 33.33%
rsvd | last 4 digits | date | starttime | endtime | rsvd | description of activities (break into small tasks) | Duration
| 5251 | 2024-11-21 | 17:00 | 21:00 |  | Debugging the skip-adder. Found a problem with the heirarichical structure of the adder. Need to add the following sparate entities: 1-FA with PG logic, 2-CSKIP block, 3- internal Cnet, 4-mux | 4
| 5251 | 2024-11-22 | 9:00 | 13:00 |  | Hand drawn the entire design and implemented the entites mentioned above. | 4
| 5251 | 2024-11-23 | 16:00 | 20:00 |  | checked the design on Quartus and found a problem with the sum connections not mapping properly. Added internal propagate, generate, carry and sum signals. | 4
| 5251 | 2024-11-24 | 9:00 | 12:00 |  | Continued working on connecting the entities corrrectly. Still have a problem with the mapping between signals and ports. | 3
| 5251 | 2024-11-24 | 16:00 | 20:00 |  | Analyzed the design and re-drawn the build on paper and found an error with the loop that generates the connections. | 4
| 5251 | 2024-11-25 | 8:00 | 12:00 |  | Editied the loop and viewd the design on Quartus to ensure mapping is done correctly. | 4
| 5251 | 2024-11-26 | 16:00 | 20:00 |  | Testing and editing the VDHL for the CarrySkip Block entities and visually checking the struture on Quartus. | 4
| 5251 | 2024-11-30 | 8:00 | 13:00 |  | Reviewd the critical path of the skip adder to calculate the delays properly. | 5
| 5251 | 2024-11-30 | 15:00 | 20:00 |  | Simulating and debugging the carry-skip. Added localized signals inside the for loop generating carry--skip block to make it compatible with ModelSim | 5
| 5251 | 2024-12-01 | 16:00 | 23:00 |  | Calculated the expected time delay and cost of carry-skip adder and brent kung. Including results in report | 7
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
44